## DataIssues
Client | Source | Issue Summary | Issue Description | Comments/ Solution | Status | Next Action | Assigned To
AbbVie | Service Level Schedules | Comparison test validation failed | 87 Metric Schedules threshold values are not valid as per the service level comparison test. i.e comparison test ‘grater is better’ but threshold values are in reverse order | Joel verified that relative service level definition has comparison test 'lower is better' in PROD | Resolved | Migrate the latest production data & verify the issue. | Srini/Ramesh
AbbVie | Service Level Defaults | SL Rules not available for required Engagement | 78 service level defaults associated to another engagement rules. | Joel has to confirm if we can copy same rules & rule sets to all engagments. | Pending | Joel will advise | Joel
AbbVie | Resource Unit Definitions | RU Definition Duplicates | 51 Duplicate resouce unit definitions | Joel advised to pick the recent records. | Resolved | Updated the code to pick the latest records. | N/A
AbbVie | Resource Unit Schedules | Pass-Through Items baseline not available | 844 Schedules BaseLine values are null | Pass-Through Items Baseline may not be available | Pending | Check with RD/Sridhar that how we need to handle Pass-Through calculations | Srini
AbbVie | Resource Unit Schedules | RU Schedule Duplicates | 56 Duplicate RU Schedules | Joel advised to pick the recent records. | Resolved | Updated the code to pick the latest records. | N/A
AbbVie | Charge Reporting Period | Charge Transaction Duplicates | 941 Duplicate charge transactions | Sridhar explianed that we should have 4 records for each transaction - 1. Expected Base Charge Amount 2. Expected Variable Charge Amount 3. Actual/Reported Base Charge Amount 4. Actual/Reported Variable Charge Amount There will not be Preload Base Charge Amount. We are not going to consider BaseCurrencyServiceCharge and BaseCurrencyDiscount for charge data migration | Resolved | Updated the code. Verify the data after the fix | Srini/Ramesh
AbbVie IT | Resource Unit Definitions | RU Definition Duplicates | 1 Duplicate resource unit definition | Joel advised to pick the recent record. | Resolved | Updated the code to pick the latest records. | N/A
AbbVie IT | Resource Unit Schedules | Pass-Through Items baseline not available | 6 Schedules BaseLine values are null | Pass-Through Items Baseline may not be available | Pending | Check with RD/Sridhar that how we need to handle Pass-Through calculations | Srini
AbbVie IT | Resource Unit Schedules | RU Schedule Duplicates | 56 Duplicate RU Schedules | Joel advised to pick the recent records. | Resolved | Updated the code to pick the latest records. | N/A
AbbVie IT | Charge Reporting Period | Charge Transaction Duplicates | 3723 Duplicate charge transactions | Sridhar explianed that we should have 4 records for each transaction - 1. Expected Base Charge Amount 2. Expected Variable Charge Amount 3. Actual/Reported Base Charge Amount 4. Actual/Reported Variable Charge Amount There will not be Preload Base Charge Amount. We are not going to consider BaseCurrencyServiceCharge and BaseCurrencyDiscount for charge data migration | Resolved | Updated the code. Verify the data after the fix | Srini/Ramesh
Astella | Process | Process code not available | 10 records Process codes are empty. We have been using code in service level definition. ServiceNow platform recognized the empty filed as null, hence service level definitions are not associated with these 10 process codes | Joel updated in Production. | Resolved | Migrate the latest production data & verify the issue. | Srini/Ramesh
Astella | Service Level Schedules | SL Schedule Duplicates | 387 Service level schedules have duplicate records for same period. So these duplicate entries ignored in ServiceNow. | Joel advised to pick the recent records. | Resolved | Updated the code to pick the latest records. | N/A
Astella | Service Level Schedules | SL Schedule Multiple Records for same period | 13 Service level schedule have multiple records for same period, so ServiceNow overridden one of the records for these 13 schedules | Joel advised to pick the recent records. | Resolved | Updated the code to pick the latest records. | N/A
Astella | Resource Unit Schedules | Pass-Through Items baseline not available | 26 Schedules baseline values are null | Pass-Through Items Baseline may not be available | Pending | Check with RD/Sridhar that how we need to handle Pass-Through calculations | Srini
Astella | Consumption Transactions | Consumption Transaction Duplicates | 57 duplicate consumption transactions | Need to understand why GWP inserts duplicate consumption transactions | Pending | Srini will check with Sridhar/Irfan/Brian | Srini
Astella | Charge Reporting Period | Charge Transaction Duplicates | 2486 Duplicate charge transactions | Sridhar explianed that we should have 4 records for each transaction - 1. Expected Base Charge Amount 2. Expected Variable Charge Amount 3. Actual/Reported Base Charge Amount 4. Actual/Reported Variable Charge Amount There will not be Preload Base Charge Amount. We are not going to consider BaseCurrencyServiceCharge and BaseCurrencyDiscount for charge data migration | Resolved | Updated the code. Verify the data after the fix | Srini/Ramesh
CCE | Process | Issue in SharePoint Process list | Process records in SharePoint list have same DB ID’s | Fix the PowerShell script to fix Process DB ID issue | Pending | Srini will check with Irfan/Brian | Srini
CCE | Process | Process code not available | 40 records Process codes are empty. We have been using code in service level definition. ServiceNow platform recognized the empty filed as null, hence service level definitions are not associated with these 10 process codes | Joel updated in Production. | Resolved | Migrate the latest production data & verify the issue. | Srini/Ramesh
HCSC | Service Level Misses | Dummy Service Level Miss record | Service level miss record has start date is 20450101. Metric Schedule end date logic needs to be reviewed to handle 20+ years future date. | Joel confirmed that this is dummy data. We can delete or exclude this record. | Resolved | N/A | N/A
HCSC | Service Level Defaults | SL Rules not available for required Engagement | 200 service level defaults associated to another engagement rules. | Joel suggested to copy rules & rule sets to all engagements for only HCSC Client. | Pending | Srini should update the code for only HCSC Client. | Srini
HCSC | Service Level Reporting Period | SLRP records engagement id zero | 125 Service level reporting period records are not associated to engagement. These records engagement ID is zero. | Fix the issue in PowerShell script | Pending | Srini will check with Irfan/Brian | Srini
HCSC | Resource Unit Definitions | RU Definition Duplicates | 96 Duplicate resouce unit definitions | Joel advised to pick the recent records. | Resolved | Updated the code to pick the latest records. | N/A
HCSC | Resource Unit Schedules | Pass-Through Items baseline not available | 477 Schedules baseline values are null | Pass-Through Items Baseline may not be available | Pending | Check with RD/Sridhar that how we need to handle Pass-Through calculations | Srini
HCSC | Resource Unit Schedules | RU Schedule Duplicates | 96 Duplicate RU Schedules | Joel advised to pick the recent records. | Resolved | Updated the code to pick the latest records. | N/A
HCSC | Scenario | Scenario Duplicates | 3 Projections Scenario records are available | Joel verified in production, there are not duplicate records. It may be issue only in Staging environment | Resolved | Migrate the latest production data & verify the issue. | Srini/Ramesh
HCSC | Charge Reporting Period | Charge Transaction Duplicates | 8779 Duplicate charge transactions | Sridhar explianed that we should have 4 records for each transaction - 1. Expected Base Charge Amount 2. Expected Variable Charge Amount 3. Actual/Reported Base Charge Amount 4. Actual/Reported Variable Charge Amount There will not be Preload Base Charge Amount. We are not going to consider BaseCurrencyServiceCharge and BaseCurrencyDiscount for charge data migration | Resolved | Updated the code. Verify the data after the fix | Srini/Ramesh
HCSC | Resource Unit Schedule Tiers | Issue with base & one of the tier upper bound | 335 schedules associated tiers upper bound is equal to base upper bound. | Joel agreed to exclude tier if the upper bound is matching with base upper bound. Updated the transformation to exclude tiers if upper bound matching with base upper bound. | Resolved | N/A | N/A
CCR | Service Level Schedules | Comparison test validation failed | 7 Metric Schedules threshold values are not valid as per the service level comparison test. i.e comparison test ‘grater is better’ but threshold values are in reverse order | Joel verified that relative service level definition has comparison test 'lower is better' in PROD | Resolved | Migrate the latest production data & verify the issue. | Srini/Ramesh
CCR | Resource Unit Definitions | Multiple RU Definitions with same code | 58 Resource units have same code but different name. | Joel suggested to use code & name to find the unique service level definitions | Pending | Sridhar recommanded to fix the code in production. Srini will follow up with Joel | Srini
CCR | Resource Unit Schedules | RU Schedule Duplicates | 13 Duplicate RU Schedules | Joel advised to pick the recent records. | Resolved | Updated the code to pick the latest records. | N/A
CCR | Resource Unit Schedules | Pass-Through Items baseline not available | 130 Schedules baseline values are null | Pass-Through Items Baseline may not be available | Pending | Check with RD/Sridhar that how we need to handle Pass-Through calculations | Srini
CCR | Resource Unit Schedules | RU Schedule Duplicates by code | 28 schedules associated resource units dups by resource unit code | Joel suggested to use code & name to find the unique service level definitions | Pending | Sridhar recommanded to fix the code in production. Srini will follow up with Joel | Srini
CCR | Charge Reporting Period | Charge Transaction Duplicates | 2847 Duplicate charge transactions | Sridhar explianed that we should have 4 records for each transaction - 1. Expected Base Charge Amount 2. Expected Variable Charge Amount 3. Actual/Reported Base Charge Amount 4. Actual/Reported Variable Charge Amount There will not be Preload Base Charge Amount. We are not going to consider BaseCurrencyServiceCharge and BaseCurrencyDiscount for charge data migration | Resolved | Updated the code. Verify the data after the fix | Srini/Ramesh
CCR | Resource Unit Schedule Tiers | Issue with base & one of the tier upper bound | 1 schedule associated tier upper bound is equal to base upper bound. | Joel agreed to exclude tier if the upper bound is matching with base upper bound. Updated the transformation to exclude tiers if upper bound matching with base upper bound. | Resolved | N/A | N/A
Scripps | Process | Issue in SharePoint Process list | 9 Processes are not available in SharePoint list | Fix the PowerShell script to fix Process DB ID issue | Pending | Srini will check with Irfan/Brian | Srini
Scripps | Process | Process Duplicates | Process has duplicate record for ‘Human Resource’ | Joel verified in production, there are not duplicate records. It may be issue only in Staging environment | Resolved | Migrate the latest production data & verify the issue. | Srini/Ramesh
Scripps | Service Level Transactions | Engagment expiration date/ Schedule end date | 190 Service level transactions start date is greater than relative engagement expiration date | Joel updated the relative engagement expiration date | Resolved | Migrate the latest production data & verify the issue. | Srini/Ramesh
Scripps | Service Level Misses | Engagment expiration date/ Schedule end date | 39 Service level misses start date is greater than relative engagement expiration date | Joel updated the relative engagement expiration date | Resolved | Migrate the latest production data & verify the issue. | Srini/Ramesh
Scripps | Service Level Reporting Period | SLRP records engagement id zero | 2 Service level reporting period records are not associated to engagement. These records engagement ID is zero. | Fix the issue in PowerShell script | Pending | Srini will check with Irfan/Brian | Srini
Scripps | Resource Unit Definitions | Resource Unit process is not available | 1 Resource Unit process is not available | Joel verified in production, it may be issue in Staging only. | Resolved | Migrate the latest production data & verify the issue. | Srini/Ramesh
Scripps | Resource Unit Schedules | Pass-Through Items baseline not available | 87 Schedules baseline values are null | Pass-Through Items Baseline may not be available | Pending | Check with RD/Sridhar that how we need to handle Pass-Through calculations | Srini
Scripps | Consumption Reporting Period | CRP records engagement id zero | 5 Consumption Reporting Period records Engagement ID's are 0 | Fix the issue in PowerShell script | Pending | Srini will check with Irfan/Brian | Srini
Scripps | Charge Reporting Period | Charge Transaction Duplicates | 5091 Duplicate charge transactions | Sridhar explianed that we should have 4 records for each transaction - 1. Expected Base Charge Amount 2. Expected Variable Charge Amount 3. Actual/Reported Base Charge Amount 4. Actual/Reported Variable Charge Amount There will not be Preload Base Charge Amount. We are not going to consider BaseCurrencyServiceCharge and BaseCurrencyDiscount for charge data migration | Resolved | Updated the code. Verify the data after the fix | Srini/Ramesh
Scripps | Resource Unit Schedule Tiers | Issue with base & one of the tier upper bound | 25 schedules associated tiers upper bound is equal to base upper bound. | Joel agreed to exclude tier if the upper bound is matching with base upper bound. Updated the transformation to exclude tiers if upper bound matching with base upper bound. | Resolved | N/A | N/A
Bloomberg | Service Level Schedules | Comparison test validation failed | 2 Metric Schedules threshold values are not valid as per the service level comparison test. i.e comparison test ‘lower is better’ but threshold values are in reverse order | Joel verified that relative service level definition has comparison test 'grater is better' in PROD | Resolved | Migrate the latest production data & verify the issue. | Srini/Ramesh
Bloomberg | Charge Reporting Period | Charge Transaction Duplicates | 119 Duplicate charge transactions | Sridhar explianed that we should have 4 records for each transaction - 1. Expected Base Charge Amount 2. Expected Variable Charge Amount 3. Actual/Reported Base Charge Amount 4. Actual/Reported Variable Charge Amount There will not be Preload Base Charge Amount. We are not going to consider BaseCurrencyServiceCharge and BaseCurrencyDiscount for charge data migration | Resolved | Updated the code. Verify the data after the fix | Srini/Ramesh